**Construction work under MPF Scheme**:-

**Cooch Behar District**.

As on 12.12.2015.

|  |  |  |
| --- | --- | --- |
| SL. No. |  Name of the Project. |  Present Status. |
| 1 | Construction of New Police Station Building at Ghoksadanga. | The construction work was approved under MPF Scheme for the year 2008-2009. The executing Agency is The Executive Engineer, Torsa Bridge Construction Division, CoochBehar. The construction work is held up due to non receipt of rectified Government Order. Proposal for rectification of G.O.No.685/PL dated.23.2.2010 has been forwarded to the Government vide Memo.no.407/Fin/B/216/09 dated.19.1.2012. of Police Directorate West Bengal. In this respect further correspondence along with fresh estimate has been made with the Govt. vide Memo.No.2422/ Fin/B dated.13.10.2014 for administrative approval and sanction of fund. In this respect last correspondence has been made with the P.D. W.B. vide this Office Memo. 3042/E dt.1.9.2015. The construction work has not yet been started. |
| 2 | Construction of Barrack (50) head at Sitalkuchi Police Station. | The construction work has been approved under MPF Scheme for the year 2011-12. The Original plan estimate submitted by the Executive Engineer, West Bengal Police Housing Corpn. Ltd. Kolkata was forwarded to the Government vide Memo.No.4959/Fin/B158-12 dated.12.10.12 of Police Directorate, W.B. for sanction of fund. Fund has been sanctioned accordingly. Work order has already been issued from WB Police Housing and Infrastructure Development Corpn.Ltd. Kolkata vide Memo.no. EnGG/MPF-11-12 /2080/ 2014/ 1049 dt.6.8.2015. Construction work up to Roof level including Roof casting has already been completed. |
| 3 | Construction of Mathabhanga P.S. Building along with Barrack & Canteen. | The construction work has been approved under MPF Scheme 2013-14. Work order has been issued from The Addl.D.G.P. (Housing) West Bengal & Managing Director, W.B.State Police Housing Corpn. vide Memo. No. Eng/MPF/2059/2013 dated.18.11.2015. The construction work has not yet been started.  |
| 4 | Construction of Force Barrack at Dinhata Police Station. | The construction work has been approved under MPF Scheme 2014-15 vide Memo.No. 2758/Fin/B dt.11.11.2014 of Police Directorate, West Bengal. Work order has been issued from the ADG(Housing) & MD WBSPHC vide Memo.No. Engg/MPF/2089/2014 dt.5.8.2015. The work has not yet been started. |
| 5 | Construction of 8(eight) L.S. quarter at Mathabhanga Police Station. | The construction work has been approved under MPF Scheme 2014-15 vide Memo.No. 2758/Fin/B dt.11.11.2014 of Police Directorate, W.B. The entire fund also already been allotted accordingly. The work will be executed by The ADG(Housing) & MD WBSPHC Limited, W.B. The construction work has not yet been started. |
| 6 | Construction of Boxirhat Police Station Building. | The construction work has been approved under MPF Scheme 2014-15 vide Memo. No. 2758/Fin/B dt.11.11.2014 of Police Directorate, West Bengal. The work order has been issed from The ADG(Housing) & MD WBSPHC Ltd. vide Memo.No.Engg/1619 dt.2.12.2015. The construction work has not yet been started. |
| 7 | Construction of Tufanganj Police Station Building. | The construction work has been approved under MPF Scheme 2014-15 vide Memo. No. 2758/Fin/B dt.11.11.2014 of Police Directorate, West Bengal. The work order has been issued from The ADG(Housing) & MD WBSPHC Ltd. vide Memo.No.Engg/2107 dt.4.12.2015. The construction work has not yet been started. |
| 8 | Construction of Rural Police Station at Sitai P.S. | The construction work has been approved in the financial year 2014/15. Work order has been issued from The ADG(Housing) & MD WBSPHC Ltd. vide Memo.No.Engg/3200/2015 dt.4.5.2015 for Rs.1,94,68,380/- only. The construction work up to roof level (excluding roof casting) has been completed. |
| 9 | Construction of changing/Rest room with toilet for women Police personnel at (i) Dinhata P.S., (ii) Mekliganj P.S., (iii) Sitalkuchi P.S. and (iv) Haldibari P.S. | The construction work has been approved under MPF Scheme in 2015/16. The work is being executed from The ADG(Housing) & MD WBSPHC Ltd. Kolkata. The construction work of Sitalkuchi P.S. has been started.  |